PREVENION OF SEXUAL EXPLOITATION AND ABUSE

YOUTH PEER EDUCATION

CONCEPT NOTE

i. Project Profile

| Project Name | Prevention of Sexual Exploitation and Abuse (PSEA) in Eswatini |
| --- | --- |
| Project Aim | Increase PSEA awareness and reporting of violations |
| Project Objectives | - Strengthen the capacity of peer educators to facilitate peer education sessions on PSEA - Increase awareness on PSEA through school and community peer education platforms and dialogues - Increase access to information on PSEA through the development and dissemination of IEC materials - Strengthen reporting and referral systems - Evaluate project impact |
| Routine Project Indicators | 1. # of Peer educators trained 2. # of adolescents and young people 10-14; 15-24 years) reached 3. # of Schools and communities reached 4. # of community members including parents/caregivers reached 5. # of IEC material developed and disseminated |
| Location | Nkilongo Constituency in the Lubombo Ref |
| Project Period | September to December 2022 |
| Target Population | 600 in and out-of-school adolescents and 300 parents and caregivers |
| Implementing Partner | Super Buddies Club |

PROJECT BACKGROUND

Super Buddies Club will implement sexual exploitation and abuse at Nkilongo Inkhundla in the Lubombo region. The project will start by recruiting 6 peer educators who are based in the 3 communities where Super Buddies Club implementation program is located. The 3 communities are as follows: Mangwaneni, Mahlabaneni and Mndobandoba community. Each community will be represented by two peer educators of Super Buddies Club. The recruited peer educators will be trained on how to create awareness on PSEA, receive community complaints and how to link PSEA with the Sexual Offenses and Domestic Violence Act (SODV 2018). The training will also include 2 staff so that they are able to assists peer educators in the field and also facilitate community dialogues.

The trained peer educators will then facilitate peer education sessions in 4 schools (two primary and two high schools) that are located within the 3 communities that will be reached through this project. The dialogues platforms will be used to reach out-of school adolescents and youth.

During the sessions, peer educators will also document issues arising from the topics that will be covered and challenges.

PURPOSE FOR FACILITATING SESSIONS

To educate and raise awareness on PSEA among adolescents and young people in and out of school in order to increase the reporting of violations.

TARGET

Young people from the age of 10-14 years and 15-24 years (both males and females)

METHODOLOGY

A peer educators facilitators module will be developed and use as a guide by the peer educators to facilitate sessions. To ensure understanding of the topics covered, the peer educators will also use role-plays and scenarios to engage the adolescents and young people in discussion on the topics.

DURATION OF SESSIONS

Each sessions will take 1 hour

OBJECTIVES

- Increase knowledge on PSEA and among adolescents and young people in and out of school

- Increase the reporting of PSEA violations by adolescents and young people in and out of school

EXPECTED RESULTS

- Increased knowledge and awareness on PSEA among adolescents and youth in Nkilongo Constituency in the Lubombo Region of Eswatini

- Increased SEA cases reported by victims and referral to relevant structures for access to services