DISSEMINATION OF INFORMATION ON PREVENION OF SEXUAL

EXPLOITATION AND ABUSE VIA WHATSAPP

CONCEPT NOTE

i. Project Profile

| Project Name | Prevention of Sexual Exploitation and Abuse (PSEA) in Eswatini |
| --- | --- |
| Project Aim | Increase PSEA awareness and reporting of violations |
| Project Objectives | - Strengthen the capacity of peer educators to facilitate peer education sessions on PSEA - Increase awareness on PSEA through school and community peer education platforms and dialogues - Increase access to information on PSEA through the development and dissemination of IEC materials - Strengthen reporting and referral systems - Evaluate impact of the project |
| Routine Project Indicators | 1. # of Peer educators trained 2. # of adolescents and young people 10-14; 15-24 years) reached 3. # of Schools and communities reached 4. # of community members including parents/caregivers reached 5. # of IEC material developed and disseminated |
| Location | Nkilongo Constituency in the Lubombo Region |
| Project Period | September to December 2022 |
| Target Population | 600 in and out-of-school adolescents and 300 parents and caregivers |
| Implementing Partner | Super Buddies Club |

INTRODUCTION

Super Buddies Club will implement sexual exploitation and abuse project at Nkilongo Inkhundla in the Lubombo region. The project will start with the training of 6 peer educators who are based in the 3 communities where Super Buddies Club will be implementating the project. The 3 communities are as follows: Mangwaneni, Mahlabaneni and Mndobandoba community.  The training will also include 2 staff members who will mentor the peer educators and also facilitate community dialogues on PSEA. The trained peer educators will then facilitate sessions on PSEA in the 4 schools. Out of school adolescent and youth will be reached through community dialogues. The social media (WhatsApp) will also be used to reach adolescents and young people who will not be reached through the sessions and dialogues. A video that will incorporate sign language will be developed and shared via WhatsApp for young people to download, watch and learn about PSEA.

TARGET

The dissemination of the video via WhatsApp will target adolescents and youth in ages 10-14 and 15-24 years including those living with disabilities.

METHODOLOGY

A consultant will be engaged to develop the video. The process will start with the development of the script that will be used as a guide in the development of the video. Upon finalization, peer educators in different WhatsApp groups will share the video for young people to have access to information on PSEA.

OBJECTIVES

- To create awareness of PSEA among adolescents and young people including those living with disabilities through social media platforms.

EXPECTED OUTCOMES

- Increased awareness on PSEA

- Increased reporting of SEA cases by targeted beneficiaries