DEVELOPMENT OF A VIDEO ON THE PREVENTION OF SEXUAL EXPLOITATION AND ABUSE IN ESWATINI

CONCEPT NOTE

i. Project Profile

| Project Name | Prevention of Sexual Exploitation and Abuse (PSEA) in Eswatini |
| --- | --- |
| Project Aim | Increase PSEA awareness and reporting of violations |
| Project Objectives | - Strengthen the capacity of peer educators to facilitate peer education sessions on PSEA - Increase awareness on PSEA through school and community peer education platforms and dialogues - Increase access to information on PSEA through the development and dissemination of IEC materials - Strengthen reporting and referral systems - Evaluate impact of the project |
| Routine Project Indicators | 1. # of Peer educators trained 2. # of adolescents and young people 10-14; 15-24 years) reached 3. # of Schools and communities reached 4. # of community members including parents/caregivers reached 5. # of IEC material developed and disseminated |
| Location | Nkilongo Constituency in the Lubombo Region |
| Project Period | September to December 2022 |
| Target Population | 600 in and out-of-school adolescents |
| Implementing Partner | Super Buddies Club |

ii. Project background

Super Buddies Club will implement the Prevention of Sexual Exploitation and Abuse (PSEA) in Nkilongo Constituency in the Lubombo Region in the Lubombo Region of Eswatini. The project begins with the training of 6 peer educators and 2 staff on the facilitation of peer education sessions on PSEA to reach in and out of schools adolescents and young people. Community dialogues on the prevention of sexual exploitation and abuse (PSEA) will be done to reach parents/caregivers and community leaders. The project will be implemented in 4 schools and in 3 communities under the Nkilongo Constituency.  Printed IEC material will be developed, printed and disseminated through peer education sessions that will be conducted in 4 schools and communities. The IEC material will include the development of a video clip that will be circulated via social media (WhatsApp) and reach adolescents who will not be reached through the peer education sessions that include those living with disabilities.

Super Buddies Club will engage a consultant to provide services on the development of a video that will be used to create awareness on the prevention of sexual exploitation and abuse via one of the social media platforms (WhatsApp). The information will target adolescents and young people in and out of school including those living with disabilities.

iii. Objective of the development of the video clip

To increase access to information on PSEA by adolescents and young people including those living with disabilities in Nkilongo Constituency in the Lubombo Region of Eswatini

iv. Scope of Work

Develop a video on the Prevention of Sexual Exploitation and Abuse in Eswatini

The consultant is expected to undertake the development of the video that will educate adolescents and young people on their rights to protection from sexual exploitation and abuse, and how and where they can report incidences of sexual exploitation and abuse. The video should be developed in simple English that will be easily understood by all beneficiaries.

Deliverables:

- Develop a script that will guide the development of the video

- Facilitate the orientation of peer educators on the development of the video

- Conduct a video shot

- Edit and submit draft production

v. Duration and time frame

The process of the development of the video production shall be expected to be completed within 5 working days.

| Deliverables | Number of days |
| --- | --- |
| Scrip development | 1 |
| Orientation of peer educators on the video shoot | 1 |
| Facilitation of video shoot | 1 |
| Editing and finalization of video | 2 |
| Total | 5 |

vi. Consultancy Competencies, Experience, and Skill Requirements:

- Minimum University degree in Health Promotion or another relevant field;

- Experience in production of video production

- Experience in working with health promotions and youth

Experience:

- At least 5 years’ experience of working with civil society organizations on public health-related issues

- Ability to work independently and deliver quality results against tight deadlines.